www.churchyouthministry.comm

Residential Planning Timeline

(First published in Premier Youthwork magazine)

Print this timeline out and stick it to your wall. The timescale is approximate. You may need to adjust it for your situation, for example if you need to book up your venue earlier. Ticking off as you do each one will allow you to tell at a glance what you need to do next and where you are behind schedule. There may be items that you need to do which aren't on the list – we have to book a ferry – but other items should remind you to do them.

| Item/Action | H-12 mths | H-6 mths | H-5 mths | H-4 mths | H-3 mths | H-2 mths | H-6 wks | H-4 wks | H-3 wks | H-2 wks | H-1 wk | H-1 day | H day | H+1 wk | H+2 wks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Visit venue (look at bedspaces, meeting room, social room, health and safety, accommodation split, door access etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix date with venue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ask church leadership to approve event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Book venue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send young people and parents 'Save the date' |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Put date in church diary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Book visiting speaker if required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Book transport if required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Invite leadership & catering team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Book any special activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange dates for planning meetings with leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check certificates (police check, first aid, food hygiene) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Core team planning meeting (including teaching theme, team challenge theme, big picture, big changes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check insurance for residential & for individual activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget event and agree with Treasurer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create Residential community on social media for leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce publicity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Put together video/slide show of last year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Set up booking online (if required) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Book van for equipment (if required) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Whole team planning meeting (overview, programme, seminar ideas (if required), roles) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send out leaders' roles and instructions, inc. speaker |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Closing date for bookings - is transport large enough? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact young people who you might have expected to book up but haven’t |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange with service leader to have feedback Sunday after residential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce themed Powerpoint and distribute to speakers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train AV operators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inform catering team of dietary requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Kit list & final details to young people & leaders with health & photo permission form |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send leaders' instructions out |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Worship team organised (if applicable) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Order bookstall (if required) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inform venue of programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send directions for venue to coach company & leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect leaders' health details |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Write risk assessments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draw up dorm lists/teams/small groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draw up buddy list if necessary for newer members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create a feedback form |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Put video clips, presentations, song words on laptop (if required) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Put branded items on laptop/ memory stick |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce booklets for young people/leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce handouts for seminars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange payment for activities with Treasurer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buy cards and presents for venue, catering team, spouses, speaker, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce dorm lists and door signs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Produce large programmes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draw up washing up rota (if required) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check first aid kit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check young people's medical forms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create list of young people whose photo cannot be taken |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check bookings for birthdays on the residential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Distribute prayer notes to church |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final planning/prayer meeting. Brief on safeguarding etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meet young people at coach and collect health forms/photo forms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect medicines, health and photo forms as people board bus |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Go to event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Return |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have people fill in feedback forms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Return borrowed items |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input/testimony in service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Send feedback form to leaders/ speaker and review event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect in final receipts and close account with Treasurer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have thank you dinner for team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

www.churchyouthministry.com Updated November 2025